## Slide 1: Railroad Towers
Issues and updates for towers proposed in railroad rights of way

## Slide 2: POSITIVE TRAIN CONTROL
Implementation deadline extended to 2018 (further extensions possible)
Railroads report that they still aim to complete environmental clearances in 2016 so they can proceed with deployment and testing ASAP
As written, the Program Comment is in effect until May 16, 2021 so no extension was required
Program Comment efficiencies:
  Certain exclusions from Section 106 review
  APE limited to ¼ mile
  Concurrent SHPO/Tribal 30-day review
  No response= referred to FCC for resolution (10 days)
  Adverse Effect Agreements can require monitoring, other provisions

## Slide 3: POSITIVE TRAIN CONTROL REVIEWS

## Slide 4: POSITIVE TRAIN CONTROL - EFFECTS
Vast majority have been cleared with no effects (or no adverse effects)
If an Adverse Effect is identified
  Explore alternative sites
  If not possible, advise FCC (email to jill.springer@fcc.gov)
  Work with SHPO and/or Tribe to determine avoidance, mitigation, or monitoring requirements
  Adverse Effect Agreement
ACHP notification
Environmental Assessment may be required

## Slide 5: POSITIVE TRAIN CONTROL - REMINDERS
If the project was approved more than a year ago, railroads should:
  Check State (SHPO) guidelines on approval expiration
  Confirm that the project to be constructed is the same as that approved
If the project changes prior to construction, advise FCC
  New review may be required
Withdrawn or Revised Projects
  E-106 and TCNS
No construction until all environmental reviews (106 and EA, if required) for actual proposed project are completed

## Slide 6: NON-PTC POLES = REGULAR NPA REVIEWS
Non-PTC poles, or PTC poles more than 75’ tall, require Section 106 review under the regular process established in the NPA.
These include, but are not limited to:
  Advanced Train Control System Poles (ATCS): fixed digital radio link between multiple base stations along railroad tracks to communicate, monitor and control trackside or wayside equipment
  PTC Base Station Poles
  WiFi Poles
  Other (RR Police Radio, etc.)

## Slide 7: GENERAL CONSIDERATIONS
Most other (non-FCC regulated) construction in railroad rights of way (e.g. double tracking, expansion, etc.) is exempted from environmental, historic preservation, and sometimes even local, reviews
The direct APE for FCC undertakings includes all (but only) work associated with the tower or pole:
  Trenching
  Staging
  Associated infrastructure (cabinets, power source, etc.)
If any recent non-FCC related construction is evident (double-tracking, signals, etc.) in photographs in the report, explain!

## Slide 8: LESSONS LEARNED
Railroads may know about cultural resources in their right of way from past experience; PTC (or other infrastructure) requires special care
  Turn of century RR construction clipped a mound site
  APE not sufficiently defined in PTC consultation
  Artifacts identified during utility trenching
  Work stopped, mitigation required (MOA)

## Slide 9: LESSONS LEARNED
When projects are delayed or modified, special care is required to ensure all parties receive notification and full information
  Project submitted as excluded PTC, then withdrawn
  New E-106 notification, but same TCNS number (no updates to TCNS)
  SHPO identified concerns and required monitoring, Tribes not adequately notified of project revisions or SHPO concerns
    Once monitoring was agreed, project should not be considered excluded
  Monitor contacted FCC to ask status of Tribal consultation
  Work stopped, adequate Tribal notification required before project proceeded

## Slide 10: RESUBMITTING OR REVISING PROJECTS
  Updating an E-106 filing (using the same number) automatically generates an email notification to the Tribes who have expressed interest in the project.
  If a NEW E-106 filing (new number) is instead made, one of the following is necessary:
    Submit a NEW TCNS notification with a statement in the Project Details box that references the original TCNS number; or
    Submit an eSupport request (https://esupport.fcc.gov/request.htm) asking the FCC to reinstate the original TCNS Number to a Proposed status and list the project changes.
    The FCC will then update the notification with the project changes and reset the notification to go back out to the Tribes.
  In either case, the contractor is required to then update the related E-106 filing to remove the initial TCNS number and recopy the new or updated TCNS notification number into the E-106 filing.

## Slide 11: LESSONS LEARNED
Expedited, streamlined PTC process still requires flexibility to protect resources
  RR proposed 65’ PTC pole in highly sensitive (and scenic) area associated with the creation story of several Tribes, considered a traditional cultural property
  Tribe requested viewshed analysis as necessary to determine effect
  Consultant referred request as not sufficiently justified
  Commission agreed with Tribe, requested railroad to review proposal
  Railroad reviewed and redesigned, moved pole out of TCP

## Slide 12: “View towards proposed pole.”

## Slide 13: WIRELESS RAILROAD INFRASTRUCTURE
QUESTIONS?